## Requirement
REQUIREMENTS TRACEABILITY MATRIX
PROJECT MANAGER: | Andrew Smith |  |  | PROJECT ID: | AX-EMEA-000302
PROJECT SPONSOR: | Mark Jones |  |  | PROJECT TITLE: | Embeded Checkout Form
REQUIREMENT INFORMATION |  |  |  |  | RELATIONSHIP TRACEABILITY
ID | CATEGORY | REQUIREMENT | PRIORITY | SOURCE | Requirement Type | DELIVERABLE(S | VALIDATION | Status
REQ-001 | Mandatory | PSP API integration | High | CTO /Architect | Technical |  | Unit/Integration/UAT testing | New
REQ-002 |  | Mapping requirements on dd/mm/yyyy format, amount, currency, file attachment. | Medium | Architect |  |  | Unit/Integration/UAT testing | New
REQ-003 | Mandatory | Customised checkout pages with delivery address and payment method for registered customers/potential buyers (user friendly interface) | Medium | Product Owner | Functional |  | Unit/Integration/UAT testing | New
REQ-004 | Mandatory | making checkout procedure easy for customer registering/logging in for the first time (User-friendly). | High | Product Owner | Functional |  | Unit/Integration/UAT testing | New
REQ-005 | Mandatory | Device Compatibility | Medium | Architect | Functional |  | Unit/Integration/UAT testing | New
REQ-006 | Mandatory | Browser compatibility with payment form display | Medium | Architect | Functional |  | Unit/Integration/UAT testing | New
REQ-007 | Mandatory | KYC (Know your Customer) Compliance | High | Product Owner/Compliance team | Service |  | Unit/Integration/UAT testing | New
REQ-008 | Should-Have | The customer enters cardholder data into the payment form and the data is sent to PSP API (tbc on SAQ A or SAQ A - EP) | Blocked | Product Owner/Finance/Compliance | Non-Functional |  | Unit/Integration/UAT testing | New
REQ-009 | Mandatory | The PSP receives cardholder data and sends it to the payment system for authorisation. | Medium | PSP/Architect | Functional |  | Unit/Integration/UAT testing | New
REQ-010 | Should-Have | Security controls - prevent any malicious attack. | High | Cyber Security Team/Architect | Non-Functional |  | Unit/Integration/UAT testing | New
REQ-011 | Mandatory | Transactions confirmation on successful /failed transactions. | High | Architect/Technical Team | Functional |  | Unit/Integration/UAT testing | New
REQ-012 | Should-Have | Reconcialition on customer transactions. | High | Service Desk | Service |  | Unit/Integration/UAT testing | New
REQ-013 | Mandatory | Integration with internal systems SAP Billing and CMS | High | Architect/PO | Non-Functional |  | Unit/Integration/UAT testing | New
REQ-014 | Should-Have | Customer experience rating | Medium | Product Owner | Functional |  | Unit/Integration/UAT testing | New
REQ-015 | Nice-To-Have | Live-Chat | Low | Architect/Service Desk | Functional |  | Unit/Integration/UAT testing | New

## Project Plan
| PROJECT TITLE |  | START DATE
| E-Commerce Payment Service |  | 2020-07-01 |  |  | PROJECT DURATION
| PROJECT MANAGER |  | END DATE |  |  | in days
| Andrew Smith |  | 2020-12-31 |  |  | 184
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT CONCEPTION AND INITIATION | In Progress | [5 empty] | Not Started
1.1 | – Project Charter | In Progress | [5 empty] | In Progress
1.1.1 | –– Project Charter Revisions | In Progress | [5 empty] | Complete
1.2 | – Research | Not Started | [5 empty] | On Hold
1.3 | – Projections | In Progress
1.4 | – Stakeholders | In Progress
1.5 | – Governance model | Not Started
1.6 | – High level budget planning | Not Started
1.7 | – Project Initiation | Not Started
2 | PROJECT DEFINITION AND PLANNING | Not Started
2.1 | – Scope & Goal Setting | Not Started
2.2 | – Setting meetings | Not Started
2.3 | – Budget review | Not Started
2.4 | – WBS | Not Started
2.5 | – Assignment | Not Started
2.6 | – Resource Palnning | Not Started
2.7 | – Communication Plan | Not Started
2.8 | – Risk Management/Risk Register | Not Started
3 | PROJECT LAUNCH & EXECUTION | Not Started
3.1 | – Mission Statement | Not Started
3.2 | – Project Controls | Not Started
3.3 | – Documentation (Functional spec, process design) | Not Started
3.4 | – Implementation (infrastructure) | Not Started
3.5 | – UX Design | Not Started
3.6 | – Development | Not Started
3.7 | – Qulaity Assurance/Quality Control | Not Started
3.8 | – KPIs | Not Started
4 | PROJECT PERFORMANCE / MONITORING | Not Started
4.1 | – Measure Performance | Not Started
4.2 | – Project tracking | Not Started
4.3 | – Change Management | Not Started
4.4 | – Risk Management | Not Started
4.5 | – Quality Control | Not Started
5 | PROJECT CLOSING | Not Started
5.1 | – Confirm work done as per requirement | Not Started
5.2 | – Gain formal acceptance | Not Started
5.3 | – Complete final performance testing/UAT | Not Started
5.4 | – update lessons learnt | Not Started

## Change Mgt
Version | Implemented | Revision | Approved | Approval | Reason
# | By | Date | By | Date
1 | <Author name> | <mm/dd/yy> | <name> | <mm/dd/yy> | <reason>
Role | Name | Contact | Description
[Insert Role] | [Insert Name] | [Insert Contact #] | [Insert Role Description]
Step | Description
Generate CR | A submitter completes a CR Form and sends the completed form to the Change Manager
Log CR Status | The Change Manager enters the CR into the CR Log. The CR’s status is updated throughout the CR process as needed.
Evaluate CR | Project personnel review the CR and provide an estimated level of effort to process, and develop a proposed solution for the suggested change
Authorize | Approval to move forward with incorporating the suggested change into the project/product
Implement | If approved, make the necessary adjustments to carry out the requested change and communicate CR status to the submitter and other stakeholders

## Change request form
Change Request Form
SUBMITTER - GENERAL INFORMATION
CR#
Submitter Name
Brief Description of Request
Date Submitted
Date Required
Priority | Low | Medium | High | Mandatory
Reason for Change
Other Artifacts Impacted
Assumptions and Notes
Attachments or References | Yes | No
Link:

## Budget
Project Budget Form
Name of Organization: | InvestigateWest
Creating Revenue Opportunities through a Radio Partnership
Name of Project:
Grant #: | [7 empty] | (For INN use only)
Proposed Start Date:
Target End Date:
|  | Revenues | [5 empty] | Notes
Project Revenues |  | Proposed | Actuals | Variance | % | Variance | %
Contributed Income
1. Individual contributions |  | $0 |  | $0
2. Corporate contributions |  | $0 |  | $0
3. Foundation grants |  |  |  | $0
a) INNovation Funds
b) Other
4. Federal government support |  |  |  | $0
5. State government support |  |  |  | $0
6. Local government support |  |  |  | $0
7. Parent organization support |  |  |  | $0
8. Special events |  |  |  | $0
9. In-kind contributions |  |  |  | $0
10. Other (specify): |  |  |  | $0
Earned Income
11. Fees for services |  |  |  | $0
12. Admissions |  |  |  | $0
13. Memberships |  |  |  | $0
14. Publications and royalties |  |  |  | $0
15. Contracted services |  |  |  | $0
16. Rentals |  |  |  | $0
17. Other (specify): |  |  |  | $0
Other Income
18. Investment |  |  |  | $0
19. Interest |  |  |  | $0
20. Other (specify) |  |  |  | $0
Total Revenues |  | $15,000 | $0 | -$15,000 | -100%
* Include expenses for THIS PROJECT ONLY on this page.
* Leave items blank that were not completed on your final proposal form.
* No depreciation expense for items purchased as part of this grant should be included.
|  | Expenses | [5 empty] | Notes
Project Expenses |  | Proposed | Actuals | Variance | % | Variance | %
1. Program salaries and wages (sub-total): |  | $5,670 | $0 | -$5,670 | -100%
Associate Director |  | $5,670 | [5 empty] | 25 percent * 4 months
2. Administrative salaries and wages (sub-total): |  | $3,544 | $0 | -$3,544 | -100%
Executive Director |  | $3,544 | [5 empty] | 15 percent * 4 months
3. Consultant/Contract services (sub-total): |  | $1,778 | $0 | -$1,778 | -100%
99designs.com |  | $1,098 | [5 empty] | Logo design; Postcard/Flyer/Print design
Focus Group Transcription |  | $680 | [5 empty] | 6 hours @ $1.85 per audio minute
5. Employee benefits |  | $645 | $0 | -$645 | -100% |  |  | @ 7% of wages
6. Adminstrative expenses |  | $0 | $0 | $0
7. Travel (sub-total) |  | $500 | $0 | -$500 | -100%
Associate Director, Seattle Kickoff |  | $500
8. Supplies and materials (sub-total) |  | $538 | $0 | -$538 | -100%
Project kickoff |  | $150 | [5 empty] | Lunch x 2 days for project kickoff
Focus group refreshments |  | $388 | [5 empty] | 6 focus groups; light refreshments
9. Rent |  | $800 | $0 | -$800 | -100% |  |  | Event space rental
10. Utilities |  | $0 | $0 | $0
11. Insurance (includes workers comp & liability) |  | $100 | $0 | -$100 | -100% |  |  | Event space insurance req.
12. Legal fees |  | $0 | $0 | $0
13. Accounting fees |  | $0 | $0 | $0
14. Other professional fees (sub-total) |  | $0 | $0 | $0
15. Taxes-payroll taxes |  | $737 | $0 | -$737 | -100% |  |  | @ 8% of wages
16. Printing and publications |  | $500 | $0 | -$500 | -100% |  |  | Event/series collateral (posters/postcards)
17. Postage and shipping |  | $0 | $0 | $0
18. Marketing |  | $0 | $0 | $0
19. Fund raising |  | $0 | $0 | $0
20. Capital expenses |  | $0 | $0 | $0
21. Overhead/indirect (specify): |  | $0 | $0 | $0
22. Depreciation |  | $0 | $0 | $0
23. Other (specify): |  | $0 | $0 | $0
Total Expenses |  | $14,811 | $0 | $14,811 | 100%

## BLANK - Project Plan Template (hidden)
PROJECT PLAN TEMPLATE
| PROJECT TITLE |  | START DATE
PROJECT DURATION
| PROJECT MANAGER |  |  |  |  | in days
1
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT CONCEPTION AND INITIATION |  |  |  |  | 1 |  | Not Started
1.1 | – Project Charter |  |  |  |  | 1 |  | In Progress
1.1.1 | –– Project Charter Revisions |  |  |  |  | 1 |  | Complete
1.2 | – Research |  |  |  |  | 1 |  | On Hold
1.3 | – Projections |  |  |  |  | 1
1.4 | – Stakeholders |  |  |  |  | 1
1.5 | – Guidelines |  |  |  |  | 1
1.6 | – Project Initiation |  |  |  |  | 1
2 | PROJECT DEFINITION AND PLANNING |  |  |  |  | 1
2.1 | – Scope & Goal Setting |  |  |  |  | 1
2.2 | – Budget |  |  |  |  | 1
2.3 | – Communication Plan |  |  |  |  | 1
2.4 | – Risk Management |  |  |  |  | 1
3 | PROJECT LAUNCH & EXECUTION |  |  |  |  | 1
3.1 | – Status & Tracking |  |  |  |  | 1
3.2 | – KPIs |  |  |  |  | 1
3.2.1 | –– Monitoring |  |  |  |  | 1
3.2.2 | –– Forecasts |  |  |  |  | 1
3.3 | – Project Updates |  |  |  |  | 1
3.3.1 | –– Chart Updates |  |  |  |  | 1
4 | PROJECT PERFORMANCE / MONITORING |  |  |  |  | 1
4.1 | – Project Objectives |  |  |  |  | 1
4.2 | – Quality Deliverables |  |  |  |  | 1
4.3 | – Effort & Cost Tracking |  |  |  |  | 1
4.4 | – Project Performance |  |  |  |  | 1
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Risks&Mitigation
SL No | Risks | Mitigation
1 | Requirements and UX Designs may not be ready prior to begin of the sprint | Requirement review meetings twice a week with PO's and DEV's to ensure designs are ready
2 | Employee1 will be out of office for 2 weeks | Employee2 will be covering Employee1 in his absence.
3 | UX Design might change after Dev starts | UX Design walk through delivered by PO to the DEV teams.
4 | Initial sizing of features are based on'T-Shirtsizes'guestimates. Actual estimates might vary | Employee3 will be re-evaluating the stories to see if any of them can be de-scoped or prioritsed lower. Employee 4 will be reviewing 'Continius Improvement' to see if it can de-scoped.
5 | Team X and Team Y are relatively new teams. Their velocity will be low. | Team support and on the job training will be provided.
6 | possible situation of 2 contractors to be removed in October . The team size will reduce | Team members from other team will be let into the team for additional support.
7 | Uncertain Covid-19 situation the payment provider terms & conditions, contract agreement, billing agreement might change, government regulations on businesses, delay in project delivery. | to be discussed with the subject matter expertise. In terms of time few weeks of buffer can be reserved.

## Governance model
Governance Group | Level of Authority
Team Leads | Changes within own team, or that are agreeable to other teams, that do not adversely impact project budget or schedule.
Change Control Board | Changes to requirements or interim milestones within the overall project budget and schedule.
Project Manager | Changes that may be accommodated within the overall project budget and schedule. [Change this to reflect your project’s decision regarding Project Manager’s authority to approve changes to scope, schedule, and budget.]
Project Director | Changes that may be accommodated <<within 5%>> of the overall project budget and schedule.
Project Sponsor | Changes that may be accommodated between <<5-10%>> of the overall project budget and schedule.
Executive Steering Committee | Changes that will require an increase to the project funding, impact implementation dates, or change project scope that have an impact of 10% or greater.
Policy related changes; contract amendments.
State Control Agencies and/or Legislature | Any changes of more than 10% of scope, schedule, or resources.
Budget action requests of any amount.
Section 11.00 requests.
Procurement of vendors.